## GanttChart
Product Road Map: Anti-Vape VR Project
Vic Health
| Project Start Date |  | 2024-07-23 |  |  |  | Display Week | 6 |  | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
[10 empty] | 2024-08-26 | [6 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14
 | time axis 2024-08-26 to 2024-10-20
WBS | TASK | MILESTONE |  | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-08-26 to 2024-10-20
1 | Initiating |  |  |  |  | - |  |  | -
1 | Initiating |  |  |  | 2024-07-23 | 2024-08-05 | 14 | 100% | 10
1.1 | Identify Stakeholders |  |  |  | 2024-07-23 | 2024-07-27 | 5 | 100% | 4
1.2 | Assign Roles |  |  | 1.1 | 2024-07-28 | 2024-07-29 | 2 | 100% | 1
1.2.1 | Initial Research |  |  | 1.2 | 2024-07-30 | 2024-08-05 | 7 | 100% | 5
2 | Planning |  |  |  |  | - |  |  | -
2 | Planning |  |  | 1.2.1 | 2024-07-30 | 2024-08-13 | 15 | 100% | 11
2.1 | Initial Client Meeting |  |  | 2 | 2024-07-30 | 2024-07-30 | 1 | 100% | 1
2.1.1 | Storyboard Development |  |  |  | 2024-07-31 | 2024-08-13 | 14 | 100% | 10
2.1.2 | Finalize Objectives & Scope |  |  |  | 2024-07-30 | 2024-08-06 | 8 | 100% | 6
2.2 | Research VR Tools for Meta Quest 3 |  |  | 2.1 | 2024-08-07 | 2024-08-13 | 7 | 100% | 5
2.3 | Setup Development Environment (Unity, Meta Quest 3 SDK) | Setup Development Environment |  | 2.1 | 2024-08-10 | 2024-08-13 | 4 | 100% | 2
3 | Executing Plan |  |  |  |  | - |  |  | -
3 | Executing Plan |  |  |  | 2024-08-13 | 2024-10-21 | 70 | 33% | 50
3.1 | Sprint 1 |  |  |  | 2024-08-13 | 2024-09-02 | 21 | 100% | 15
3.1.1 | Create Foundational Layout & Interface |  |  | 2.3 | 2024-08-13 | 2024-08-19 | 7 | 100% | 5
3.1.2 | Implement Initial VR Interactions |  |  | 3.1.1 | 2024-08-17 | 2024-08-28 | 12 | 100% | 8
3.1.3 | Develop Vape Creation Feature | Creation of Vape object with interactions possible |  | 2.3 | 2024-08-15 | 2024-08-19 | 5 | 100% | 3
3.1.4 | Add Visual (Text) Representations of Harmful Substances |  |  | 2.3 | 2024-08-19 | 2024-08-26 | 8 | 100% | 6
3.1.3 | Toggle Between Healthy & Damaged Tissues | Basic representation of effects of vape on respiratory system shown |  | 2.3 | 2024-08-15 | 2024-08-24 | 10 | 100% | 7
3.1.4 | Develop Alpha Version |  |  | 3.1.3 | 2024-08-20 | 2024-08-22 | 3 | 100% | 3
3.1.5 | Test Alpha Version | Vape usability and depressing environment shown |  | 3.1.4 | 2024-08-23 | 2024-08-25 | 3 | 100% | 1
3.1.6 | Release Alpha Version |  |  | 3.1.5 | 2024-08-25 | 2024-09-02 | 9 | 100% | 6
3.2 | Sprint 2 |  |  |  | 2024-09-03 | 2024-09-30 | 28 | 0% | 20
3.2.1 | Collect User Feedback |  |  | 3.1.6 | 2024-09-03 | 2024-09-04 | 2 | 0% | 2
3.2.2 | Make it more user friendly | Provided detailed instructions for the non gamers to engage into the VR experience without External assistance |  | 3.2.1 | 2024-09-05 | 2024-09-11 | 7 | 50% | 5
3.2.3 | Phase 2 Planning |  |  | 3.1.6 | 2024-09-03 | 2024-09-09 | 7 | 0% | 5
3.2.4 | Cardiovascular System Simulation | Cardiovascular system developed with basic effects |  | 3.2.3 | 2024-09-10 | 2024-09-24 | 15 | 0% | 11
3.2.5 | Central Nervous System & Addiction Simulation | Central nervous system developed with basic effects |  | 3.2.3 | 2024-09-15 | 2024-09-24 | 10 | 0% | 7
3.2.6 | Develop beta Version |  |  | 3.2.5 | 2024-09-25 | 2024-09-27 | 3 | 0% | 3
3.2.7 | Test beta Version |  |  | 3.2.6 | 2024-09-27 | 2024-09-29 | 3 | 0% | 1
3.2.8 | Release beta Version | Effects on Respitory, CardioVasular and Central nervous system displayed and instructions provided for non gaming users |  | 3.2.7 | 2024-09-30 | 2024-09-30 | 1 | 0% | 1
3.3 | Sprint 3 |  |  |  | 2024-10-01 | 2024-10-21 | 21 | 0% | 15
3.3.1 | Phase 3 Planning |  |  | 3.2.8 | 2024-10-01 | 2024-10-03 | 3 | 0% | 3
3.3.2 | Include Interactive Withdrawal Symptoms | Withdrawal systems displayed |  | 3.3.1 | 2024-10-01 | 2024-10-14 | 14 | 0% | 10
3.3.3 | Integrate Educational Narratives |  |  | 3.3.1 | 2024-10-07 | 2024-10-16 | 10 | 0% | 8
3.3.4 | Finetuning graphics and functionality to make it more advanced | Better models developed and advanced features developed |  | 3.3.1 | 2024-10-15 | 2024-10-19 | 5 | 0% | 4
3.3.5 | Create Advance Layout & Interface |  |  | 3.3.1 | 2024-10-04 | 2024-10-17 | 14 | 0% | 10
3.3.6 | Develop Final Version |  |  | 3.3.5 | 2024-10-16 | 2024-10-19 | 4 | 0% | 3
3.3.7 | Test Final Version |  |  | 3.3.6 | 2024-10-19 | 2024-10-20 | 2 | 0% | 0
3.3.8 | Release Final Version | Fine tuned with better models replaced on basic ones |  | 3.3.7 | 2024-10-21 | 2024-10-21 | 1 | 0% | 1
4 | Final Delivery & Closure |  |  |  |  | - |  |  | -
4.1 | Final Adjustments Based on Feedback |  |  | 3.3.8 | 2024-10-21 | 2024-10-22 | 2 | 0% | 2
4.2 | Deliver Final Version to Client & Impliment | Final Version |  | 4.1 | 2024-10-23 | 2024-10-25 | 3 | 0% | 3
4.3 | Complete Project Documentation | Documentation |  | 4.2 | 2024-10-25 | 2024-10-31 | 7 | 0% | 5
5 | Closing |  |  |  |  | - |  |  | -
5.1 | Conduct Product Demonstration | Demonstration |  | 4.2 | 2024-11-01 | 2024-11-01 | 1 | 0% | 1
5.2 | Sign Off the Contract | Signoff |  | 5.1 | 2024-11-02 | 2024-11-02 | 1 | 0% | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.